## Project Timeline
PROJECT TIMELINE TEMPLATE
AT RISK | SPIN | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | COMMENTS | STATUS
| Sprint 1 | Phân tích yêu cầu | Complete | Hưng, Khánh | 20/03/2025 | 31/03/2025 | 11 |  | Not Started
| Sprint 1 | Thiết kế hệ thống | Complete | Lâm, Huy | 25/03/2025 | 2025-05-04 | 11 |  | In Progress
Medium | Sprint 2 | Phát triển module thu tiền | In Progress | Khôi, Hưng | 2025-04-03 | 2025-04-04 | 31 |  | Complete
Low | Sprint 2 | Phát triển module điện nước | In Progress | Huy, Khánh | 2025-05-04 | 15/04/2025 | 10 |  | On Hold
High | Sprint 3 | Tích hợp hệ thống | Not Started | Lâm, Khôi | 16/04/2025 | 28/04/2025 | 12
| Sprint 3 | Kiểm thử chức năng | Not Started | Khánh, Huy | 29/04/2025 | 2025-10-05 | 12
| Sprint 4 | Triển khai thử nghiệm | Not Started | Hưng, Lâm | 2025-11-05 | 20/5/2025 | 9

## BLANK - Project Timeline
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS KEY
Not Started
In Progress
Complete
On Hold
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*